## Sheet1
To do list of the Vision-Assist Project
Sl.no | Task Name | Assigned | Status | Started | Finished | Development | Testing
1 | Real-Time Currency Recognition | Akash T | In progress (98%) | 2024-07-29 |  | Mostly completed(Need to improve accuracy)
2 | Text Reading | Muhammed Hidash | In progress (94%) | 2024-07-29 |  | Mostly completed(Need to improve accuracy)
3 | Activity Recognition | Archana G S | In progress (98%) | 2024-07-30 |  | Completed | Ongoing
4 | Frontend |  | In progress
| 1.Integration of camera in to the app and taking the picture | Sahal Muhammed K K | Completed | 2024-07-30 | 2024-07-13 | Completed | Completed
| 2. Welcome message and instruction | Sahal Muhammed K K | Completed | 2024-07-02 | 2024-07-14 | Completed | Completed
| 3. UI of spacial description | Sahal Muhammed K K | In progress(60%) | 2024-07-19
| 4. UI of object detection |  | In progress(50%) | 2024-07-21
| 5. UI of Text Reading |  | In progress(50%) | 2024-07-21
6. UI of familiar face reconition
| 7. UI of Human Activity recognition |  | In progress(50%) | 2024-07-21
| 8. UI of currency identification |  | In progress(50%) | 2024-07-22
5 | Voice Feedback and Interaction | Archana G S | In progress(80%) | 2024-07-19
6 | Object identification | Akash T | Completed | 2024-07-15 | 2024-07-02 | Completed | Ongoing
7 | Spatial Description
8 | Facial Recognition | Muhammed Hidash | In progress(80%) | 2024-07-19
9 | model integration to app(server)
10 | API Integration